## HM Project Plan
Ministry Serology Implementation Plan
Region/Ministry |  |  | Accountable executive
Responsible Team | Task | Assigned to | Due date | Status | Document title to support task
Clinical Team | Identify the accountable clinical executive and send name of executive leader to your Incident Command leader.
Partner with local National Health Ministry (home care, senior communities, TH PACE) leaders to ensure that their colleagues are included within the prioritization of colleague cohorts.
Prioritize colleague populations for first rounds of testing
Partner with clinical leaders and lab directors to determine colleague testing process (unit based, outpatient draw stations, etc.)
Determine process for ordering test
Identify clinician(s) responsible for ordering test. This person will order for all Trinity Health colleagues within their state, including System Office, Continuing Care, etc. If you region covers multiple states, you may need to identify an ordering clinician in each state.
Determine process for ordering (blanket order in EMR, paper requisitions, etc.)
Confirm reporting via EMR as primary method as preferred method of sharing results with colleagues; identify secondary method should colleague not have portal
Identify resource for responding to colleague questions regarding results
Partner with local communications team to update standard templates with ministry processes and ensure
National Health Ministries | Identify the accountable national clinical executive for your ministry and local leader for each location
Partner with local HM Clinical and HR teams to ensure colleague testing plans are aligned.
Communicate serology testing plan to colleagues.
Human Resource Team | HM Human Resources leaders should be aware of plans and ensure they meet colleague needs and any applicable legal requirements.
Partner with NHM Human Resources leaders to ensure that their colleagues’ needs are met.
Ensure proper forms and documentation are available and used properly.
Finance Team | All colleague testing should be charged to the 81205-COVID-19 cost center.
Follow the Billing and Accounting Guidance for Sereology Testing for Colleagues file.
Communications Team | Update standard templates to reflect ministry processes
Develop cadenced communications to colleagues
Send communications to colleagues
Email Jody Lamb and Rachel Nelson of System Office Communication the final communication files and timing for communicating them
Lab Team | Set up orders and results functionality (LIS/EMR), submit request to IT
Order reagents from vendor
Notify the PM by email when the reagent has been received
Add new test to analyzer test menu
Validate new test method per policy
Test orders interface to validate results reporting
Test code and charge code validation
If EUA, patient and provider sheets need to be distributed in the communication.
Affirm the results reporting processes
Health Informatics and IT | Confirm/update applicable process flows and related documentation
Conduct or participate in end-user testing and validation efforts in collaboration with lab team
Create/update any site-specific job aids or EHR end-user functionality guides
Communicate process changes to key stakeholders in the RHM
Assess and evaluate end-user readiness and adoption of change